## Safety Code
Cycling Ireland Event Safety Code
SAFETY CODE
• Cycling Ireland require that all events run under its regulations take place in an environment that is safe for participants, event personnel and general public. It is recognised that owing to the nature of events run under its regulations (e.g., road races, downhill races, non-competitive events etc.) it is extremely difficult to eliminate all risks. Safety is the responsibility of event organisers, event personnel and participants and everyone has a role to play in ensuring we adequately manage risks that cannot be eliminated.
• This Safety Code applies to events run under the auspices of a Cycling Ireland affiliated club, Commission, Provincial Executive or Sub-Committee
1. GENERAL GUIDELINES
• An Event Organiser must appoint a Safety Officer, the Event Organiser may also be the Safety Officer. The Safety Officer should be selected based on experience, competence, control, cooperation and communication.
• The Event Organiser is responsible for appointing a Safety Officer and for the implementation of this Safety Code. The Safety Officer should:
- Be present at planning meetings;
- Assist in the preparation of the Risk Assessment;
- Act in an advisory capacity on safety issues;
- Implement safety measures to reduce identified risks and be in attendance at event itself;
- Liaise as necessary with relevant authorities.
• In applying this Safety Code Event Organisers/Safety Officers must recognise that the degree of risk involved will vary depending
on factors such as the number of participants, experience of participants, nature of route, whether the event is of a competitive nature etc. For example there is a large difference between a mass-participation event of 4,000 (relatively) inexperienced cyclists and a club race of 30 experienced cyclists.
• Marshals are to be made aware of their role and responsibilities as outlined in the Cycling Ireland sign-on sheet (“.... function of the marshal is only to indicate direction”)
and any special requirements recognised in the Risk Assessment.
• A pre-event briefing, which may be verbal and/or written, must be provided to participants. The pre-event briefing should cover (as applicable)
- The requirement for participants to abide by the rules of the road;
- Responsibility of participants to be mindful of their own safety and the safety of others;
- An outline of the course and any particular hazards such as junctions, descents, poor surfaces, etc.;
- The distance, number of laps to be covered, prime locations etc.
• A Risk Assessment (see appendix 2 as an example) must be completed by the Safety Officer. The purpose of a Risk Assessment is
to identify hazards and measures that reduce the risk posed by hazards to an acceptable level.
2. Traffic/Course Safety
Traffic and course hazards probably pose the greatest risks
and Event Organisers must put in place steps to minimise the risk and inconvenience to traffic which may encounter the event and also to minimise the risk posed by the course itself. Steps to be considered include:
• Local authorities to be advised, as per local authority
requirements, in advance of road usage - provide route maps, dates, times, likely number of participants, number of separate events etc.;
• Garda/P.S.N.I. to be informed in line with required regulations (it is advised to notify Garda/P.S.N.I.) at least twelve weeks prior to the event;
• Lead vehicle(s) (sufficient to cover breaks that may form) with appropriate signage and lighting to warn oncoming traffic of the event, road user’s should be warned where there are sizeable groups;
• Consider appointment of motorbike marshals to aid the safe passage of participants;
• The course must be reconnoitred and marshals appointed at appropriate locations;
• Only those deemed competent by the Safety Officer are to be appointed as marshals;
• Each marshal point must be contactable by mobile phone/two-way radio;
• Marshals should be equipped with a hi-vis vest, whistle and flag;
• Warning signs placed as appropriate advising the general public an event is in progress;
• Warning signs placed as appropriate advising participants of particular hazards;
• Directional arrows to be provided warning of junctions;
• Advance warning to local residents through the use of signs, local newspapers, local radio;
• Particular consideration should be given to start/finish areas;
• A Risk Assessment for the course must be completed and any additional controls identified put in place - see example attached as appendix 2;
• For off-road events particular attention should be paid to reducing the risk posed by steep drops, wooden surfaces, tree-trunks, gate-posts, roots, stumps, rocks etc.;
• The Safety Officer should review the Risk Assessment and satisfy themselves that all safety measures are in place.
3. First Aid/Medical Cover
All open events (as per Cycling Ireland’s General Administrative and Technical Regulations - “A race open to holders of full
licences and/or restricted licences where appropriate and/or one day licences (excluding holders of club licences) which have been approved by the Cycling Ireland”) require, as a minimum, first aid personnel to be in attendance. The Safety Officer must assess the level of first aid required, steps to be considered include:
• Is an ambulance required or are trained First Aiders sufficient;
• Is it best for the ambulance/First Aiders to follow the participants or be placed at strategic locations?;
• Brief first aid personnel (a First Aider is a person over 18 years old who holds a first aid certificate) on route details, likely hazards, event duration;
• Ensure that first aid crew are easily contactable and test communications prior to the event start;
• For mass-participation events ensure that participants are issued a “helpline” number;
• Advise local hospitals of the event;
• participant numbers, nature of the event etc.;
• Ensure all marshals are aware of the first aid/emergency contact number;
• Ensure that contact numbers for local hospitals, ambulance support crews are to hand.
4. Participants and Event Personnel
• Participants must:
- Have a bicycle that is in good working order (which complies with relevant Technical Regulations);
- Wear a hard-shell helmet;
- Be mindful of the need to act in a manner that takes account of their own safety and the safety of others;
- Ensure their fitness level is appropriate given the nature of the event;
- Ensure their nutritional requirements can be met;
- Be conversant with and obey the rules of the road;
- Familiarise themselves with the event route;
- “Sign-on” for the event;
- Be aware that marshals are not empowered to stop traffic;
- For downhill, BMX events wear full personal protection equipment - full-face helmets are compulsory;
• Commissaires are responsible for the general sporting organisation of a race and not for safety, however a Commissaire may, if dissatisfied on any matter of safety, take action as they deem appropriate;
• Event personnel should:
- Be of a responsible age;
- Be appropriately briefed and clear as to their role;
- Wear any PPE (e.g., hi-vis vest) as identified in the Risk Assessment;
- Remain at their post until informed that they are no longer required;
- “Sign-on” for the event.

## Timetable
Appendix 1
Timetable for Event Organisers
Pre- Calendar Deadline
Apply to Cycling Ireland for a calendar date as per the instructions issued by Cycling Ireland.
Four Months Before
Go over the course and identify any changes since the completion (if any) of the previous Risk Assessment and complete a preliminary Risk Assessment; Identify and book race headquarters (ideally with changing and shower facilities), for off-road events confirm with landowner; Book first aid cover; Notify (and provide required information to) relevant local authorities and Garda/P.S.N.I.; Book other equipment as required - photo-finish, PA system, finish podium, barriers, race radios, catering, media coverage, signage, lead vehicles, neutral support, cars;
Preceding Week and On the Day
Finalise the Risk Assessment; Check that there have been no late hazards - road-works, sweep any identified loose debris if practicable, etc.; Have directional signs to the race HQ in place; Ensure that warning signs are in place; Cash float for sign-on desk, pins, stationery (sign-on sheets etc.); Place route markers on route; Display route details, information on particular hazards; Brief all personnel and participants; Submit results to Cycling Ireland; Pay expenses to Commissaires etc.; Note details of any incidents (time, place, contact details for those involved, nature of incident and any injuries suffered) and advise Cycling Ireland of details; Clean the start/finish areas, race route and race HQ; Check all participants for valid licences.
Aftermath
Send letters of thanks as appropriate to local authorities, Garda, sponsors, first aiders etc.; Note any improvements for future events; Remove any signs, barriers etc. erected for the event.

## Event Details Risks
Appendix 2
EVENT DETAILS RISK ASSESSMENT
Name of Event:
Event Organiser and Contact Details:
Event Safety and Contact Details:
Event Date(s):
Type of Event (road race, leisure spin, downhill, etc.)
Risk/Hazard | Suggested measures to mitigate risk | Mitigating actions taken
TRAFFIC SAFETY CODE
Not a lawful event - relevant authorities (Garda, P.S.N.I., local authorities, landowners) not notified | • Notify local authorities Garda, P.S.N.I.,landowners as appropriate
Conflict with other events in locality | • Enquire with local authorities • Arrange for additional cover as required through towns, junctions etc.
Residents unaware of event | • Provide advance warning of event
Unexpected hazards (e.g. roadworks, adverse weather conditions etc.) | • Arrange for roadworks to be rectified, alternative route • Pre-race inspectors and sweep hazardous loose debris • Additional marshals
No route Risk Assessment performed | • Perform route Risk Assessment - see appendix 3 as an example and appendix 4 as template
Unexpected late hazards (e.g. roadworks etc.) | • Conduct route inspection as close as practical to event start and sweep hazardous loose debris • Deploy additional marshals • Carry out deviation
General public unaware of event | • Lead car(s) with flashing lights • Motorbike marshals • Signage • Marshals in place wearing vis vests
Start/finish area | • Clearly defined start/finish areas • Safe location for start/finish areas (on a straight section of road, good surface etc.) • Adequate stewarding • Parking restrictions • Barriers as required • Presentation podium placed so as not to present a traffic hazard
Off-road hazards | • Use of netting, fluorescent paint (biodegradable), straw bales • Marshals
FIRST AID/MEDICAL COVER
Inadequate first aid/medical cover | • Appoint competent, and sufficient for size of event, first aid/medical personnel as required • Advise local hospitals of event • Ensure relevant contact numbers are to hand
Inability to communicate | • Ensure all key marshals, Safety Officer and First Aid are contactable by radio and/or cell phone (see appendix 6)
PARTICIPANTS
Participants not following route | • Route map available • Directional arrows • General awareness of route • Provide a contact number in the event that participants are in difficulty
Dehydration/exhaustion | • Provide refreshment points • Provide a contact number in the event that participants are in difficulty
Injuries resulting from crashes | • Hazards reduced through route risk assessment • Compulsory wearing of helmets • Deployment of first aid/medical support
Mechanical breakdowns | • Provide mechanical support • Provide a contact number in the event that participants are in difficulty
Participants not insured | • Event to be sanctioned by Cycling Irelnd and therefore fall under Cycling Ireland’s insurance scheme • All participants to ‘sign-on’
OTHER HAZARDS
Scalding from hot water | • Hot water to be kept in a segregated area, canteen personnel to exercise caution
Slips, trips and falls | • All areas to be kept free of clutter • Adequate number of refuse bins
Use of generator - manual handling, fire, noise | • Competent, traind personnel only to operate generator • Barrier around generator • Generator inspected periodically • Caution exercised when filling with fuel - gloves worn, in well-ventilated area • Fire-fighting instructions provided along with fire- fighting material • Noise kept to a minimum
Overcrowding | • Ensure there are adequate number of marshals

## RA Example
Appendix 3
Example of Route Assessment
STAGE 1: MILLTOWN AND GLENCAR
Start Killorglin at 3:30pm, 2nd April 2010 | [7 empty] | Estimated time of arrival at:
[8 empty] | 32.5KPH 20MPH | 39KPH 24 MPH | 45KPH 28 MPH
KM | MILES | LOCATION |  | RISK | INSTRUCTION | STEPS TO REDUCE RISK | RACEPLAN | 15:30 | 15:30 | 15:30
0 | 0 | The Square, Killorglin |  | L | Race start |  |  | 15:30 | 15:30 | 15:30
0.3 | 0.2 | Roundabout |  | M | 3rd exit dir. Killarney | Moto Marshal |  | 15:30 | 15:30 | 15:30
0.3 | 0.2 | Roundabout |  | M | 3rd exit dir. Killarney | Moto Marshal |  | 15:30 | 15:30 | 15:30
0.3 | 0.2 | Roundabout |  | M | 3rd exit dir. Killarney | Moto Marshal |  | 15:30 | 15:30 | 15:30
0.8 | 0.5 | 60km sign |  | L | End of control zone. Race Start | Chief Commissaire/Timekeeper |  | 15:31 | 15:31 | 15:31
5.2 | 3.2 | Blind junction LHS |  | H | Straight ahead | Moto Marshals |  | 15:39 | 15:38 | 15:36
12 | 7.4 | Beaufort Bridge |  | M | Straight ahead | Moto Marshals |  | 15:52 | 15:48 | 15:45
12.2 | 7.5 | Lahard X LHS |  | L | Straight ahead | Moto Marshals |  | 15:52 | 15:48 | 15:46
12.7 | 7.8 | Blind junction LHS |  | M | Straight ahead | Moto Marshals |  | 15:53 | 15:49 | 15:46
16.4 | 10.1 | Golden Nugget |  | L | Straight ahead | Moto Marshals |  | 16:00 | 15:55 | 15:51
17.9 | 11 | Golf Club Entrances LHS + RHS |  | L |  | Moto Marshals |  | 16:03 | 15:57 | 15:53
19.8 | 12.2 | Roundabout |  | M | 1st exit dir. Tralee | Static Marshals/ Moto Marshals/Gardaí | Garda Arrows Straight ahead | 16:06 | 16:00 | 15:56
20.5 | 12.6 | Roundabout |  | M | 1st exit dir. Tralee | Static Marshalls/Moto Marshals/Gardai | Garda Arrows Left | 16:07 | 16:01 | 15:57
21.3 | 13.1 | 100km sign |  | L | Straight ahead |  |  | 16:09 | 16:02 | 15:58
26 | 16 | Lawlors X |  | L | Straight ahead | Moto Marshals |  | 16:18 | 16:10 | 16:04
28.9 | 17.8 | Start of KOH Opposite the garage at bottom of hill |  | L | Straight ahead |  | Start of KOH Sign Opposite the garage at bottom of hill | 16:23 | 16:14 | 16:08
30.4 | 18.7 | KOH primeline |  | L | Straight ahead | KOH Judge | KOH sign | 16:26 | 16:16 | 16:10
33.6 | 20.7 | 50km sign Farrenfore |  | L | Straight ahead |  |  | 16:32 | 16:21 | 16:14
34.1 | 21 | Center Farrenfore |  | M | Turn left onto R561 | 4 x Static Marshals, Moto Marshals, Garda | Garda Arrows Left | 16:33 | 16:22 | 16:15
35.4 | 21.8 | Level Crossing |  | L | Straight ahead |  |  | 16:35 | 16:24 | 16:16
37.1 | 22.8 | Traffic Island |  | M | Straight ahead | 2 x Static Marshals with flags and whistles | Caution signs
37.5 | 23.1 | Firies Village Caution Sharp Left |  | H | Turn left | Static Marshals at junction from Church, 1 from the houses across from pub and 1 at bridge, Moto Marshals | Arrows Left Caution signs | 16:39 | 16:27 | 16:19
38.2 | 23.5 | HolyCross |  | L | Keep left | Moto Marshals to cover junction on bend
45.3 | 27.9 | Junction |  | M | Keep right | Moto Marshals to cover junction on bend
48.1 | 29.6 | Brackhill X |  | L | Straight ahead | Moto Marshals | Arrows straight ahead | 16:53 | 16:39 | 16:29
48.1 | 29.6 | Milltown Centre |  | M | Turn left and then turn right | Static Marshals: 1@ Killarney side of junction, 1@ Killorglin side of junction | Garda/Arrows right/ Caution signs | 16:58 | 16:44 | 16:33
48.3 | 29.7 | Milltown Bridge Start of KOH |  | L | Straight ahead |  | Start of KOH Sign On the bridge | 16:59 | 16:44 | 16:33
48.8 | 30 | 100km sign KOH Prime Line Cat 4 |  | L | Straight ahead | KOH Judge |  | 17:00 | 16:45 | 16:34
52.2 | 32.1 | Kennedys X |  | L | Straight ahead | Moto Marshals | KOH Sign | 17:06 | 16:50 | 16:38
53.1 | 32.7 | Junction LHS |  | L |  | Moto Marshals |  | 17:08 | 16:51 | 16:40
53.6 | 33 | Bansha X junction LHS |  | L | Straight ahead | Moto Marshals |  | 17:09 | 16:52 | 16:40
54 | 33.2 | 60km sign |  | L | Straight ahead |  |  | 17:09 | 16:53 | 16:41
55.1 | 33.9 | Roundabout: Caution Traffic Island Centre of road |  | M | 3rd exit dir. Killorglin | 1 x Static Marshals @traffic Island, Gardaí @ roundabout | Garda (if available) Arrows Right! Caution signs starting before Chubs Corner | 17:11 | 16:54 | 16:42
55.3 | 34 | Bianconi X |  | M | Turn Right | Gardaí and 2 x Static Marshals | Garda Arrows Right | 17:12 | 16:55 | 16:42
55.4 | 34.1 | Church Corner/Market Street junction |  | M |  | 1 Static Marshal at Church corner and 1 at Market Street junction | Garda
55.7 | 34.3 | Roundabout |  | M | 1st exit dir Cahersiveen | Gardaí and 2 x marshals | Garda Arrows Straight ahead | 17:12 | 16:55 | 16:43
56.7 | 34.9 | 100km sign |  | L |  |  |  | 17:14 | 16:57 | 16:44
64 | 39.4 | Red Fox Bar |  | L | Straight ahead | Moto marshals | Arrows Left from the pub to the Junction | 17:28 | 17:08 | 16:54
64.2 | 39.5 | Quaybawn X, Caution: very sharp turn |  | M | Turn left Very acute turn | 2 x Static Marshals/Moto Marshals | Arrows Left Caution Signs | 17:28 | 17:08 | 16:54
64.4 | 39.6 | Caution Sharp right + sharp Left |  | M | Old level crossing | Moto Marshals | ! Caution signs | 17:28 | 17:09 | 16:54
KM | MILES | LOCATION | RISK |  | INSTRUCTION | STEPS TO REDUCE RISK | RACEPLAN | 15:30 | 15:30 | 15:30
64.8 | 39.9 | Bowlers X | H |  | Turn Right | 2 x Static Marshals/ Moto Marshals hold all traffic here until the race passes through | Arrows Right | 17:29 | 17:09 | 16:55
72.3 | 44.5 | Start of KOH | L |  |  |  | Start of KOH Sign | 17:43 | 17:21 | 17:05
73.6 | 45.3 | KOH Prime line Cat 3 Peach coloured bunglow RHS | L |  |  | KOH Judge | KOH Sign | 17:45 | 17:23 | 17:07
75.1 | 46.2 | Caution Sharp right + sharp Left over narrow bridge | H |  | Caution | 1 x Static Marshal with flag and whistle | ! Caution signs | 17:48 | 17:25 | 17:09
76.7 | 47.2 | Blackstones Bridge | M |  |  | 2 x Static Marshals |  | 17:51 | 17:28 | 17:11
|  | Holding place Blackstones Bridge | M |  |  | 2 Moto Marshals to move well ahead of the race on the climb to the KOH. And move to the far side of Blackstones Bridge. Hold all cars here until the race has passed through
75.1 | 46.2 | Junction on bend Caution lots of fast but narrow bends for 0.5 miles | H |  | Keep right | Lots of arrows | Arrows Right ! Caution signs | 17:48 | 17:25 | 17:09
79.5 | 48.9 | The Rowan Tree Bar X Traffic Holding | M |  | Straight ahead | Note to Moto Marshals: all traffic is to be held at a wide point on the road until the main bunch passes |  | 17:56 | 17:32 | 17:14
80.9 | 49.8 | T - Junction | L |  | Turn left | 2 x Static Marshals/ Moto Marshals | Arrows Left | 17:59 | 17:34 | 17:16
82.4 | 50.7 | Holding place Road widens near the lake | M |  |  | Note to Moto Marshals: all traffic is to be held at a wide point on the road until the main bunch passes |  | 18:02 | 17:36 | 17:18
84.2 | 51.8 | Holding place Old Quarry | M |  |  | Note to Moto Marshals: all traffic is to be held at a wide point on the road until the main bunch passes |  | 18:05 | 17:39 | 17:21
85.6 | 52.7 | Holding Place Space at the road side RHS | M |  |  | Note to Moto Marshals: all traffic is to be held at a wide point on the road until the main bunch passes |  | 18:08 | 17:41 | 17:22
90.4 | 55.6 | Humpback bridge | H |  | Straight ahead | 2 x Static Marshals | ! Caution signs | 18:16 | 17:49 | 17:29
93.1 | 57.3 | Owenagarry X | L |  | Straight ahead | Moto Marshals |  | 18:21 | 17:53 | 17:32
93.9 | 57.8 | Gormons X | L |  | Straight ahead | Moto Marshals |  | 18:23 | 17:54 | 17:33
94.7 | 58.3 | T junction to Annadale Road | L |  | Turn left | 2 x Static Marshals | Arrows Left | 18:24 | 17:55 | 17:34
0 | 59 | Bianconi X | M |  | Turn left | Gardaí and 2 x Static Marshals | Garda Arrows Left | 18:27 | 17:57 | 17:36
96.2 | 59.2 | Finish The Square Killorglin | L |  |  |  |  | 18:27 | 17:58 | 17:36

## Risk Assessment
Appendix 4
KMS | LOCATION | DIRECTION TO TAKE | HAZARD | RISK (H-high, M-medium, L-low) | STEPS TO REDUCE RISK TO LOW | RACE/ADDITIONAl NOTES | ETA (first passage) | ETA (last passage)

## Safety Checklist
Appendix 5
Event Safety Checklist
Event: |  |  | Total Distance: KM LAPS OF: KM
EVENT OFFICIALS | CHECK | COMMENTS |  | NAME | MOBILE PH | RADIO
Race Director
Safety Officer
Chief Marshal
Commissaire 1
Commissaire 2
Commissaire 3
EMERGENCY SERVICES | CHECK | COMMENTS |  | NAME | MOBILE PH | RADIO
Ambulance
First Aid
General
Doctor 1 On Call
Doctor 2 On Call
Hospital 1 On Call
Hospital 2 On Call
Fire Brigade (RTA) Local Garda/P.S.N.I.
OTHER MEASURES | CHECK | COMMENTS |  | NAME | MOBILE PH | RADIO
Circuit Traffic & Traffic Management
Stop/go system if required
Lead cars - signs on car, lights on etc
Course inspected
Course markings - directional and warnings
Start/Finish - barriers, crowd control etc
Gardai/P.S.N.I. in Attendance
Marshals (static and mobile) - hi-vis vests flags and whistles
Race communication - radios in place and tested, mobile numbers
Briefings given to participants and officials
Riders support - neutral service, broom wagon

## Contact Details
Appendix 5
Event Personnel Contact Details
KM /Mls | Location | Instructions | ROLE: (Static marshal, Motorbike marshal, lead car driver etc.) | Marchal Name (S) | Radio # | MOBILE # | SIGNATURE